## Sheet1
BUG Report
Bug ID | Summary | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority
OpenCart-Bug-1 | Thank you Registering' email is not recived to registered mail-id | "1.Click on 'My Account' Drop Down Menu 2.Click on Register option 3.Fill new account details into Mandatory fields 4.Click on Continue button 5.Check the mail 6.Click on the 'Verify the mail' in email " | Email should sent to register mail id and it should have link that takes to the home page of the website | User account getting created but user didn't get any mail to the register email-id | Major | P1(Mediam)
OpenCart-Bug-2 | User is abel to register an account by providing invalid phone number. | 1.Click on 'My Account' Drop Down Menu 2.Click on Register option 3.Enter all the details into the fields. 4.Enter invalid Phone Number 5.Click on Continue button | Account should not be created instead a warning message should appear like "Invalid Phone Number". | It creating an account instead of giving Warning message like "Invalid Phone Number". | Major | P1(Mediam)
OpenCart-Bug-3 | Privacy Policy is not marked with star symbol | 1.Click on 'My Account' Drop Down Menu 2.Click on Register option 3.Check wether all the mandatory fields have a star mark or not | All mandatory fields should have star mark | Privacy Policy is not marked with star symbol | Minor | P2(Low)
OpenCart-Bug-4 | A Password field should give message "Password should contain special character". | 1.Click on 'My Account' Drop Down Menu 2.Click on Register option 3.Enter all the details in fields. 4.Click on Continue button | A Password field should give message "Password should contain special character". | A Password field should give message "Password should contain special character". | Major | P1(Mediam)
OpenCart-Bug-5 | There is no EYE symbol in the Password field. | 1.Click on 'My Account' Drop Down Menu 2.Click on Register option 3.Check whether the Password field have EYE symbol or not. | EYE symbol should be there in the Password field. | There is no EYE symbol in the Password field. | Minor | P2(Low)
OpenCart-Bug-6 | Password no follwing the Password Complexity Standards. | 1.Click on 'My Account' Drop Down Menu 2.Click on Login option 3.Enete the mail & password 4.Click on Login Button | Password should follw the Password Complexity Standards. | Password no follwing the Password Complexity Standards. | Minor | P2(Low)
OpenCart-Bug-7 | There is no EYE symbol in the Password field. | 1.Click on 'My Account' Drop Down Menu 2.Click on Login option 3.Check whether the Password field have EYE symbol or not. | EYE symbol should be there in the Password field. | There is no EYE symbol in the Password field. | Major | P2(Low)
OpenCart-Bug-8 | A warning message is not appeared that "Your account has exceeded no.of attempts". Please try again later. | 1.Click on 'My Account' Drop Down Menu 2.Click on Register option 3.Enter Invalid Email 4.Enter Invalid Password 5.Click on Login button 6.Repeate 4 or 5 times | A warning message should appearthat "Your account has exceeded no.of attempts". Please try again later. | A warning message is not appeared that "Your account has exceeded no.of attempts". Please try again later. | Minor | P2(Low)
OpenCart-Bug-9 | A confirmation message is not appear like "Your password has changed". | 1.Click on 'My Account' 2.Click on 'Change Password' 3.Enter the New Password 4.Enter the Confirm Password. 5.Click on Continue button | A confirmation message should appear like "Your password has changed". | A confirmation message is not appear like "Your password has changed". | Minor | P2(Low)
OpenCart-Bug-10 | A Password is changing but messag is not popup. | 1.Click on 'My Account' 2.Click on 'Change Password' 3.Enter the New Password 4.Enter the Confirm Password. 5.Click on Continue button | A Password should not change and message should appear like 'this password is already in use. | A Password is changing but messag is not popup. | Minor | P2(Low)
OpenCart-Bug-11 | A message is not appear under the Password field like "Password must be between 4 and 20 characters!" It accepting more than 20 characters | 1.Click on 'My Account' 2.Click on 'Change Password' 3.Enter the New Password more than 20 characters 4.Enter the Confirm Password more than 20 characters. 5.Click on Continue button | A message should appear under the Password field like "Password must be between 4 and 20 characters!" | A message is not appear under the Password field like "Password must be between 4 and 20 characters!" It accepting more than 20 characters | Major | P1(Mediam)
OpenCart-Bug-12 | User can't be abel to redirect to the page where it allows login. | 1.Click on 'My Account' Drop Down Menu 2.Click on Login option 3.Enter Valid Mail & Password 4.Click on Login Button 5.Click on My Account Drop Down. 6.Click on Logout. 7.Check whether the page redirect to the page where it allows login? | User should be abel to redirect to the page where it allows login. | User can't be abel to redirect to the page where it allows login. | Minor | P2(Low)
OpenCart-Bug-13 | Email did not recevied | 1. Click on 'Forgotten Password' link from Login page 2. Enter the email address of an existing account. 3. Click on 'Continue' button | An email should be recivied to the registered email address with the details of resetting the password | Email did not recevied | Critical | P0(High)
OpenCart-Bug-14 | No Message got displayed | 1. Click on the reset password link available in the Login Page 2.Enter a registered mail id 3.Click on continue. | A proper message should apper like "Check your mail id to reset the password" | No Message got displayed | Minor | P2(Low)
OpenCart-Bug-15 | No warning is displayed | 1. Click on 'Forgotten Password' link from Login page 2. Don't enter anything into the 'E-Mail Address' field 3. Click on 'Continue' button (Verify ER-1) | 1. Field level warning message with text - E-Mail must be between 4 and 20 characters!' should be displayed for 'E-Mail Address' field | No warning is displayed | Major | P1(Mediam)
OpenCart-Bug-16 | No warning is displayed | 1. Click on 'Forgotten Password' link from Login page 2. Enter any invalid formatted email address into the 'E-Mail Address' field. | 1. Field level warning message informing the User to provide a valid formatted email address should be displayed | No warning is displayed | Major | P1(Mediam)
OpenCart-Bug-17 | A Payment Method field dosen't have option like "Online Payment". | 1.Click on Checkout option. 2.Go to the Payment Method. 3.Check whether the Pyment Method option have two option like "Online Payment" and "Cash On Develevry". | A Payment Method field should have two option like "Online Payment" and "Cash On Develevry". | A Payment Method field dosen't have option like "Online Payment". | Minor | P1(Mediam)
OpenCart-Bug-18 | The selected Amount from the "Flat Rate" is not reflected in the Caluclation table. | 1.Click on Checkout option. 2.Select amount from drop down in the "Flat Rate". | The selected Amount should reflect in the Caluclation table. | The selected Amount from the "Flat Rate" is not reflected in the Caluclation table. | Major | P1(Mediam)
OpenCart-Bug-19 | Wish List apge is not navigated to the home page, after clicking the continue button | 1. Click on the product 2. Click on Heart option to add product into "Wish List". 3. Click on the Wrong Button option. 4.Click on Continue button | Wish List page should navigate to the home page | Wish List apge is not navigated to the home page, after clicking the continue button | Minor | P2(Low)
OpenCart-Bug-20 | Product not displayed instead showing, like "Internal Server Error!" | 1. Enter any existing product name into the 'Search' text box field. 2. Click on the button having search icon (Verify ER-1) | 1. Searched product should be displayed in the search results | Product not displayed instead showing, like "Internal Server Error!" | Major | P1(Mediam)
OpenCart-Bug-21 | Getting a message like "nternal Server Error!" | 1. Enter non existing product name into the 'Search' text box field . 2. Click on the button having search icon (Verify ER-1) | 1. 'There is no product that matches the search criteria' should be displayed in the Search Results page | Getting a message like "nternal Server Error!" | Major | P1(Mediam)
OpenCart-Bug-22 | 1. Searched product is not displayed in the search results | 1. Enter any existing product name into the 'Search' text box field - <Refer Test Data> 2. Click on the button having search icon (Verify ER-1) | 1. Searched product should be displayed in the search results | 1. Searched product is not displayed in the search results | Minor | P2(Low)
OpenCart-Bug-23 | Shoppin cart page is not displayed | 1. Click on 'Site Map' footer option 2. Click on 'Shopping Cart' link in the displayed 'Site Map' page | 1. User should be taken to the Shopping Cart page | Shoppin cart page is not displayed | Minor | P2(Low)
OpenCart-Bug-24 | No proper message shown after click the Apply Coupon button | 1.Click on the "Use Coupon Code" on the Shopping cart page. 2.Don't enter the details 3.Click on Apply Coupon button | The field level warning should come that "This field id required" | No proper message shown after click the Apply Coupon button | Minor | P2(Low)
OpenCart-Bug-25 | Veriffy the "Use Gift Certificate" functionality in the shoppin cart page without entering the detials in the field | 1.Click on the "Use Gift Cerificate" on the Shopping cart page. 2.Don't enter the details 3.Click on Apply Gift Certificate button | The field level warning should come that "This field id required" | Getting the Success message | Major | P1(Mediam)
OpenCart-Bug-26 | 1. Success message not get displayed | 1. Click on 'Modify your wish list' option 2. Click on 'Add to Cart' icon option (Verify ER-1) | 1. Success message with text - 'Success: You have added Product Name to your shopping cart!' should ge displayed | 1. Success message not get displayed | Major | P1(Mediam)
OpenCart-Bug-27 | User did not redirected to the login page and User got redirected to the 'News letter Subscription' page | 1. Click on 'Newsletter' Right Column option (Verify ER-1) 2. Enter valid credentials and login (Verify ER-2) | 1. User should be taken to 'Login' page 2. User should be directly taken to 'Newsletter Subscription' page | User did not redirected to the login page and User got redirected to the 'News letter Subscription' page | Minor | P2(Low)